## Cover Sheet
| Document Title: | Document # | Revision | Effective Date
| OM_Medical Device_Pathpoint® eDerma | RF | 1 | 2024-04-25
Review and Approval By
| Name | Signature | Date
Authored By | Balamurugan S | BM | 2024-04-24
Approved By | Piyush Mahapatra | PM | 2024-04-25
Revision History
Revision Level |  | DCR# |  | Effective Date
1 |  | Initial Release |  | 2024-04-25

## Risk File
| Document Title: | Document # | Revision | Effective Date
| OM_Medical Device_Pathpoint® eDerma_Risk File | RF | 1 | 2024-04-25
Source of Hazard | Hazard ID | Hazardous Situation (Description of Risk) | Describe Foreseeable Sequence Leading to Hazardous Situation | Risk ID | Describe the Harm due to the Hazardous Situation | Initial Severity Score (S) | Initial Probability of Occurance Score (O) | Initial Risk Priority Number (S*O) | Current/Planned Risk Mitigations | Risk Control Category | Mitigation Traceability | Residual Severity Score (Post Mitigation) | Residual Probability of Occurance (Post Mitigation) | Residual RPN | Risk Benefit Analysis
Usability | H001 | User confusion leading to incorrect input. | User confusion due to a non-intuitive design, leading to incorrect data entry or misuse. | R001 | Incorrect patient-reported data leading to inaccurate clinical decisions and compromised patient care. | 2 | 3 | 6 | Provide user training on system usage | Training, Usability Study | Usability Report | 2 | 2 | 4 | NA
Usability | H002 | Misinterpretation of interface elements causing data entry errors. | User confusion due to a non-intuitive design, leading to incorrect data entry or misuse. | R002 | Incorrect patient-reported data leading to inaccurate clinical decisions and compromised patient care. | 2 | 3 | 6 | Improve user interface design to enhance clarity and usability | Design Process, Usability Study | Usability Report; Design documentation; V and V | 2 | 2 | 4 | NA
Design | H003 | Incompatibility issues causing data transmission errors. | Incompatibility issues on certain devices, potentially causing data transmission errors or loss. | R003 | Data transmission errors may result in incomplete or inaccurate patient records, impacting clinical assessments. | 3 | 3 | 9 | Conduct compatibility testing across various devices | Design Process | Design documentation; V and V | 3 | 1 | 3 | NA
Design | H004 | Device-specific vulnerabilities leading to unauthorised access. | Incompatibility issues on certain devices, potentially causing data transmission errors or loss. | R004 | Data transmission errors may result in incomplete or inaccurate patient records, impacting clinical assessments. | 2 | 4 | 8 | Implement device-specific security measures | Design Process | Design documentation; V and V | 2 | 2 | 4 | NA
Software | H005 | Breach of data security during transmission. | Breach of data security during transmission, compromising patient confidentiality and privacy. | R005 | Breach of data security could lead to unauthorised access, compromising patient confidentiality and privacy. | 4 | 3 | 12 | Enhance data encryption during transmission | Software Design Complying to ISO 62304 Standard | Design documentation; V and V | 3 | 1 | 3 | NA
Software | H006 | Data loss or compromise due to inadequate encryption measures. | Breach of data security during transmission, compromising patient confidentiality and privacy. | R005 | Breach of data security could lead to unauthorised access, compromising patient confidentiality and privacy. | 4 | 3 | 12 | Strengthen encryption protocols to prevent data compromise | Software Design Complying to ISO 62304 Standard | Design documentation; V and V | 3 | 1 | 3 | NA
Regulatory | H007 | Non-compliance leading to legal consequences. | Non-compliance with regulations, resulting in legal implications and compromised patient safety. | R006 | Non-compliance may result in legal consequences, financial penalties, and reputational damage. | 3 | 3 | 9 | Establish regulatory compliance monitoring processes | Design Process | Design documentation; V and V | 3 | 2 | 6 | NA
Regulatory | H008 | Failure to adapt to evolving regulatory standards. | Non-compliance with regulations, resulting in legal implications and compromised patient safety. | R006 | Non-compliance may result in legal consequences, financial penalties, and reputational damage. | 2 | 3 | 6 | Regularly update software to meet evolving regulatory standards | Design Process | Design documentation; V and V | 2 | 2 | 4 | NA
Functional | H009 | System errors causing failure in delivering critical notifications. | Failure to receive critical notifications due to system errors or misconfigurations. | R007 | Failure to receive critical notifications may lead to missed appointments or delayed healthcare interventions. | 2 | 2 | 4 | Implement redundancy in critical notification systems | Process, Usability Study | Usability Report; Design documentation; V and V | 2 | 2 | 4 | NA
Functional | H010 | Inconsistent notification preferences leading to missed alerts. | Failure to receive critical notifications due to system errors or misconfigurations. | R007 | Failure to receive critical notifications may lead to missed appointments or delayed healthcare interventions. | 2 | 2 | 4 | Allow users to customise notification preferences | Process, Disclaimer, Usability Study | Usability Report; Design documentation; V and V | 2 | 2 | 4 | NA
Usability | H011 | Overreliance on reminders causing patient annoyance. | Overreliance on reminders leading to patient annoyance or potential disregard for important notifications. | R008 | Overreliance on reminders may cause patient annoyance, potentially leading to disengagement with the reporting process. | 2 | 3 | 6 | Balance reminder frequency to avoid user annoyance | Software Design Complying to ISO 62304 Standard, Training | Usability Report; Design documentation; Regulatory Compliance | 2 | 2 | 4 | NA
Usability | H012 | Technical issues leading to the failure of reminder notifications. | Overreliance on reminders leading to patient annoyance or potential disregard for important notifications. | R008 | Overreliance on reminders may cause patient annoyance, potentially leading to disengagement with the reporting process. | 2 | 3 | 6 | Regularly maintain reminder notification systems | Software Design Complying to ISO 62304 Standard, Training | Usability Report; Regulatory Compliance | 2 | 2 | 4 | NA
IFU | H013 | Inadequate explanation causing patient mistrust. | Inadequate explanation of data usage and privacy, causing patient mistrust or legal issues. | R009 | Inadequate explanation of data usage and privacy may lead to patient mistrust and ethical concerns. | 2 | 4 | 8 | Provide clear and comprehensive explanations to users | Software Design Complying to ISO 62304 Standard, Training | Usability Report; Design documentation; Regulatory Compliance | 2 | 2 | 4 | NA
IFU | H014 | Failure to obtain explicit consent leading to legal issues. | Inadequate explanation of data usage and privacy, causing patient mistrust or legal issues. | R009 | Inadequate explanation of data usage and privacy may lead to patient mistrust and ethical concerns. | 2 | 4 | 8 | Obtain explicit consent from users for data usage | Software Design Complying to ISO 62304 Standard, Training | Regulatory Compliance | 2 | 2 | 4 | NA
Software | H015 | Data loss or corruption affecting the accuracy of patient-reported outcomes. | Data loss or corruption, impacting the accuracy of patient-reported outcomes. | R010 | Data loss or corruption may result in inaccurate patient-reported outcomes, affecting treatment decisions. | 4 | 3 | 12 | Implement data backup mechanisms to prevent loss or corruption | Software Design Complying to ISO 62304 Standard, Business Continuity Exercise as per ISO 27001 Standard | Regulatory Compliance | 3 | 1 | 3 | NA
Software | H016 | System failure leading to the inability to save progress. | Data loss or corruption, impacting the accuracy of patient-reported outcomes. | R010 | Data loss or corruption may result in inaccurate patient-reported outcomes, affecting treatment decisions. | 4 | 3 | 12 | Implement auto-save features to prevent data loss during failures | Software Design Complying to ISO 62304 Standard, Business Continuity Exercise as per ISO 27001 Standard | Regulatory Compliance; Design documentation | 3 | 1 | 3 | NA
Security | H017 | Unauthorised access due to weak access controls. | Unauthorised access or mishandling of patient data due to system vulnerabilities. | R011 | Unauthorised access may lead to privacy breaches, compromising patient confidentiality and trust. | 2 | 4 | 8 | Strengthen access control mechanisms to prevent unauthorised access | Software Design Complying to ISO 62304 Standard, Authentication Requirement as per ISO 27001 Standard, Training | Regulatory Compliance; Design documentation | 2 | 2 | 4 | NA
Security | H018 | Mishandling of patient data permissions leading to privacy breaches. | Unauthorised access or mishandling of patient data due to system vulnerabilities. | R011 | Unauthorised access may lead to privacy breaches, compromising patient confidentiality and trust. | 2 | 4 | 8 | Enforce strict data handling policies and permissions | Software Design Complying to ISO 62304 Standard, Authentication Requirement as per ISO 27001 Standard, Training | Regulatory Compliance | 2 | 2 | 4 | NA
Documentation | H019 | Incomplete or inaccurate information causing user confusion. | Incomplete or inaccurate information in the help center, leading to user confusion. | R012 | Incomplete or inaccurate information in support resources may cause user confusion, impacting software utilisation. | 3 | 3 | 9 | Regularly update and review support resources | Design Process, Training | Usability Report; Design documentation; V and V | 3 | 2 | 6 | NA
Documentation | H020 | Lack of timely updates leading to outdated support resources. | Incomplete or inaccurate information in the help center, leading to user confusion. | R012 | Incomplete or inaccurate information in support resources may cause user confusion, impacting software utilisation. | 2 | 3 | 6 | Establish a schedule for timely updates to support resources | Design Process, Training | Usability Report; Design documentation; V and V | 2 | 2 | 4 | NA
Functional | H021 | Incorrect patient filtering impacting patient care. | Incorrect patient filtering or organisation, potentially impacting patient care. | R013 | Incorrect patient filtering may lead to oversight in patient care, potentially affecting treatment plans. | 2 | 3 | 6 | Enhance patient filtering mechanisms to prevent errors | Software Design Complying to ISO 62304 Standard, Training | Usability Report; Regulatory Compliance | 2 | 2 | 4 | NA
Functional | H022 | Data mismanagement leading to confusion in patient lists. | Incorrect patient filtering or organisation, potentially impacting patient care. | R013 | Incorrect patient filtering may lead to oversight in patient care, potentially affecting treatment plans. | 2 | 3 | 6 | Implement clearer data management protocols | Software Design Complying to ISO 62304 Standard, Training | Regulatory Compliance | 2 | 2 | 4 | NA
Design | H023 | Misalignment of customised questionnaires with patient needs. | Misalignment of customised questionnaires with patient needs, affecting data accuracy. | R014 | Misalignment of customised questionnaires may result in data inaccuracies, impacting clinical assessments. | 2 | 4 | 8 | Align questionnaires with patient needs based on feedback | Software Design Complying to ISO 62304 Standard, Training | Usability Report; Regulatory Compliance | 2 | 2 | 4 | NA
Design | H024 | Incorrect application of customisation affecting data accuracy. | Misalignment of customised questionnaires with patient needs, affecting data accuracy. | R014 | Misalignment of customised questionnaires may result in data inaccuracies, impacting clinical assessments. | 2 | 4 | 8 | Provide training on customisation features | Software Design Complying to ISO 62304 Standard, Training | Usability Report; Regulatory Compliance | 2 | 2 | 4 | NA
Functional | H025 | Data synchronisation errors leading to incomplete patient records. | Data synchronisation errors between the application and the hospital's EHR system. | R015 | Data synchronisation errors may result in incomplete patient records, affecting comprehensive patient care. | 3 | 3 | 9 | Improve data synchronisation protocols to ensure completeness | Software Design Complying to ISO 62304 Standard | Regulatory Compliance | 3 | 2 | 6 | NA
Functional | H026 | Inability to access EHR data impacting comprehensive patient care. | Data synchronisation errors between the application and the hospital's EHR system. | R015 | Data synchronisation errors may result in incomplete patient records, affecting comprehensive patient care. | 3 | 3 | 9 | Establish redundant access points for EHR data | Software Design Complying to ISO 62304 Standard | Regulatory Compliance | 3 | 2 | 6 | NA
Usability | H027 | Misinterpretation of visualised data affecting medical decisions. | Misinterpretation of visualised data, potentially leading to incorrect medical decisions. | R016 | Misinterpretation of visualised data may lead to incorrect clinical decisions and compromised patient care. | 2 | 4 | 8 | Provide training on data visualisation interpretation | User Training, User Manual | Usability Report | 2 | 2 | 4 | NA
Training | H028 | Lack of training leading to improper use of visualisation tools. | Misinterpretation of visualised data, potentially leading to incorrect medical decisions. | R016 | Misinterpretation of visualised data may lead to incorrect clinical decisions and compromised patient care. | 2 | 3 | 6 | Offer comprehensive training on visualisation tools | User Training, User Manual | Usability Report | 2 | 2 | 4 | NA
Training | H029 | Inadequate training causing misunderstanding of software functionalities. | Inadequate training leading to HCPs misunderstanding software functionalities. | R017 | Inadequate training may lead to HCPs misunderstanding software functionalities, potentially compromising patient care. | 3 | 3 | 9 | Develop and provide thorough training materials | Software with Inbuilt Support Request | Regulatory Complinace; Design documentation | 3 | 2 | 6 | NA
Training | H030 | Lack of continuous training updates affecting HCP proficiency. | Inadequate training leading to HCPs misunderstanding software functionalities. | R017 | Inadequate training may lead to HCPs misunderstanding software functionalities, potentially compromising patient care. | 2 | 3 | 6 | Establish a continuous training program for healthcare providers | Software with Inbuilt Support Request | Regulatory Complinace; Design documentation | 2 | 2 | 4 | NA
Support | H031 | Unavailability of support causing delays in issue resolution. | Unavailability of support, causing delays in issue resolution and potential patient care disruption. | R018 | Unavailability of support may cause delays in issue resolution, potentially affecting patient care. | 2 | 3 | 6 | Ensure availability of round-the-clock support | Software Development, Usability | Regulatory Complinace; Design documentation; Usability Report | 2 | 2 | 4 | NA
Support | H032 | Insufficient support resources impacting overall user satisfaction. | Unavailability of support, causing delays in issue resolution and potential patient care disruption. | R018 | Unavailability of support may cause delays in issue resolution, potentially affecting patient care. | 2 | 3 | 6 | Expand support resources to meet user demands | Software Development, Usability | Regulatory Complinace; Design documentation; Usability Report | 2 | 2 | 4 | NA
Functional | H033 | Errors in automated data entry leading to inaccuracies. | Errors in automated data entry, leading to inaccuracies in patient records. | R019 | Errors in automated data entry may lead to inaccurate patient records, affecting clinical assessments. | 4 | 3 | 12 | Implement validation checks to minimise automated data entry errors | Software Design Complying to ISO 62304 Standard, Usability Testing as per IEC 62366 | Regulatory Complinace; Design documentation | 3 | 2 | 6 | NA
Functional | H034 | System failure causing disruption in automated data entry processes. | Errors in automated data entry, leading to inaccuracies in patient records. | R019 | Errors in automated data entry may lead to inaccurate patient records, affecting clinical assessments. | 4 | 3 | 12 | Develop failover mechanisms to handle system failures | Software Design Complying to ISO 62304 Standard, Usability Testing as per IEC 62366 | Regulatory Complinace; Design documentation; Usability Report | 3 | 2 | 6 | NA
Interoperability | H035 | Insufficient integration with EHR systems leading to data inconsistency | Inadequate integration protocols result in data synchronisation failures between the eDerma platform and EHR systems. | R020 | Inconsistent patient data between the eDerma platform and EHR systems may lead to incorrect diagnoses or treatment plans. | 3 | 3 | 9 | Enhance interoperability protocols for seamless data exchange | Software Design Complying to ISO 62304 Standard, Business Continuity Exercise as per ISO 27001 Standard | Regulatory Complinace; Design documentation | 3 | 2 | 6 | NA
Scalability | H036 | Lack of scalability in handling increased patient load | Increased usage of the eDerma platform overwhelms the system, causing slowdowns or crashes. | R021 | System slowdowns or crashes due to scalability issues may disrupt patient care and lead to delays in diagnosis or treatment. | 4 | 3 | 12 | Upgrade system infrastructure to handle increased loads | Software Design Complying to ISO 62304 Standard, Business Continuity Exercise as per ISO 27001 Standard | Regulatory Complinace; Design documentation | 4 | 1 | 4 | NA
Security | H037 | Inadequate cybersecurity measures leaving patient data vulnerable | Weak cybersecurity protocols make patient data susceptible to unauthorised access or breaches. | R022 | Unauthorised access or breaches of patient data due to inadequate cybersecurity measures may compromise patient privacy and trust in the platform. | 4 | 3 | 12 | Strengthen cybersecurity measures to protect patient data | Software Design Complying to ISO 62304 Standard, Authentication Requirement as per ISO 27001 Standard, Training | Regulatory Complinace; Design documentation | 4 | 1 | 4 | NA
Interoperability | H038 | Lack of interoperability with other healthcare systems | Incompatibility with other healthcare systems prevents seamless data exchange and collaboration. | R023 | Inability to exchange data seamlessly with other healthcare systems may hinder communication among healthcare providers and impede patient care coordination. | 3 | 3 | 9 | Improve interoperability standards to facilitate data exchange | Software Design Complying to ISO 62304 Standard, Authentication Requirement as per ISO 27001 Standard, Training | Regulatory Complinace; Design documentation | 3 | 2 | 6 | NA
Usability | H039 | Complexity in user interface hindering user adoption | Overly complex user interface design makes it difficult for users to navigate and perform tasks efficiently. | R024 | Difficulty in navigating the platform due to complex user interface design may result in user frustration and reduced adoption among healthcare professionals. | 3 | 3 | 9 | Simplify user interface design for easier adoption | Design Process | Design documentation | 2 | 2 | 4 | NA
Usability | H040 | Insufficient error handling mechanisms leading to data loss | Inadequate error handling procedures result in data loss during critical operations. | R025 | Data loss during critical operations due to insufficient error handling mechanisms may compromise patient data integrity and clinical decision-making. | 3 | 3 | 9 | Implement robust error handling mechanisms to prevent data loss | Design Process | Regulatory Complinace; Design documentation | 3 | 1 | 3 | NA

## Risk Report Final
| Document Title: | Document # | Revision | Effective Date
| OM_Medical Device_Pathpoint® eDerma | RF | 1 | 2024-04-25
Hazard Description | No of Identified Risks | Evaluation |  |  | Acceptable / Unacceptable
|  | Low | Medium | High
Usability | 6 | 6 | 0 | 0 | Acceptable
Design | 4 | 4 | 0 | 0 | Acceptable
Software | 5 | 5 | 0 | 0 | Acceptable
Regulatory | 2 | 1 | 1 | 0 | Acceptable
Functional | 8 | 6 | 2 | 0 | Acceptable
Security | 3 | 3 | 0 | 0 | Acceptable
Documentation | 2 | 1 | 1 | 0 | Acceptable
Interoperability | 2 | 0 | 2 | 0 | Acceptable
Scalability | 1 | 1 | 0 | 0 | Acceptable
Training & IFU | 5 | 4 | 1 | 0 | Acceptable
Support | 2 | 2 | 0 | 0 | Acceptable
Total Hazards | 40 | 33 | 7 | 0 | Acceptable
Overall Risk Benefit Analysis: | No formal risk benefit analysis is deemed necessary since all identified risks have been mitigated to an acceptable level. However, it's noted that there are minor clinical risks that will be addressed through post-market surveillance
Describe Production and Post Production Data Methods in Place:
1. Post-Market Surveillance:
Continuous Monitoring: | Our post-market surveillance (PMS) process involves continuous monitoring of the product's performance and safety once it's deployed in the market. This includes gathering feedback from users, monitoring adverse events, and analysing real-world usage data to identify any potential issues or safety concerns.
Adverse Event Reporting: | We have established mechanisms for users and stakeholders to report adverse events or incidents encountered during product usage. These reports are carefully reviewed and investigated to determine the root cause and assess any potential risks to patient safety or product effectiveness.
Regulatory Compliance: | Our PMS activities are conducted in compliance with regulatory requirements and guidelines. We ensure timely reporting of any adverse events to regulatory authorities and take appropriate corrective actions as necessary to address identified risks.
Risk Assessment and Mitigation: | The data collected through post-market surveillance activities are used to perform risk assessments and prioritise mitigation efforts. This may involve implementing software updates, issuing safety communications, or revising product labeling to enhance safety and usability.
2. Customer Support:
Dedicated Support Team: | We have a dedicated customer support team available to assist users with any questions, issues, or concerns they may have regarding the product. Our support representatives are trained to provide timely and effective assistance to ensure a positive user experience.
Multi-channel Support: | Users can reach our customer support team through various channels, including phone, email, and online chat. We also provide self-service resources such as knowledge bases and user forums to empower users to find answers to common questions independently.
Ticketing System: | We utilise Jira, a robust ticketing system, to track and manage customer requests and support tickets. Each customer inquiry or issue is logged as a Jira ticket, allowing our support team to efficiently prioritise, assign, and track the resolution of each request.
SLA Adherence: | We adhere to service level agreements (SLAs) to ensure timely response and resolution of customer inquiries and issues. Our support team follows established protocols and workflows to meet or exceed SLA targets and provide high-quality support services.
Overall, our post-market surveillance process and customer support system are integral parts of our commitment to product quality, safety, and customer satisfaction. By proactively monitoring product performance, addressing user feedback, and providing responsive customer support, we strive to ensure the continued success of our product in meeting the needs of our users and maintaining compliance with regulatory requirements.

## Risk Report (hidden)
| Document Title: | Document # | Revision | Effective Date
| OM_Medical Device_Pathpoint Outcomes_Risk File | FORM_10.02 | A0
Hazard Description | # Identified Risks | Evaluation |  |  | Acceptable/ Unacceptable
|  | Low | Medium | High
Biological Hazard | 0 |  |  |  | NA
Chemical Hazard | 0 |  |  |  | NA
Functional Hazard |  |  |  |  | Acceptable
Operational Hazard |  |  |  |  | Acceptable
Mechanical Hazard | 0 |  |  |  | NA
Labeling Hazard |  |  |  |  | Acceptable
Electromagnetic Hazard | 0 |  |  |  | NA
Biocompatability Hazard | 0 |  |  |  | NA
Thermal Hazard | 0 |  |  |  | NA
Fire Hazard | 0 |  |  |  | NA
Clinical Hazard |  |  |  |  | Acceptable
Cybersecurity Hazard |  |  |  |  | Acceptable
Use Error Hazard |  |  |  |  | Acceptable
Overall Risk Benefit Analysis: Provide Detail of Risk Benefit Analysis at the overall system level
Describe Production and Post Production Data Methods in Place: Provide details on how the production and post production data will be monitored and how analysis of those data provide input towards risk analysis
Review and Approval
Review by | Name | Date | Sign
Approved by | Name | Date | Sign

## Not for review (hidden)
| Document Title: | Document # | Effective Date
| Risk File and Report | OM_Medical Device_Risk File | Not Yet
Source of Hazard | Hazard Description | Hazard ID | Describe foreseeable sequence leading to hazardous situation | Risk ID | Describe the Harm due to the hazardous situation | Initial Severity Score (S) | Initial Probability of Occurance Score (O) | Initial Risk Priority Number (S*O) | Current/Planned Risk Mitigations | Risk Control Category | Mitigation Traceability | Residual Severity Score (Post Mitigation) | Residual Probability of Occurance (Post Mitigation) | Residual RPN | Risk Benefit Analysis | https://www.cognitiveclouds.com/insights/7-common-risks-and-solutions-for-mobile-app-security/ | cloud problem, data lost
|  |  | The user may not be able to read and understand the instruction | R001 | Device Misuse | 2 | 2 | 4 | 1. The software application will be designed in such a way that the fonts are clearly visibile and legible for a normal human eye 2. Clear instructions for use will be given in the software application for users | Design Control and Instructions | 1. Design Control 2. IFU | 1 | 1 | 1 | NA
|  |  | User will not be able to debug issues | R002 | User Annoyance | 3 | 2 | 6 | 1. The software application will be properly designed with troubleshooting mechanism for small errors and will be tested properly | Software design complying to ISO 62304 Standard | Design Control | 1 | 1 | 1 | NA
|  |  | Users health information will be exposed | R003 | 1. Data/Security breach of users | 3 | 4 | 12 | The software application will be designed in such a way that other applications cannot track data of oursoftware application | Software Design | Design Control | 2 | 2 | 4 | NA
|  |  | The user may not be able to understand the warning | R001 | Device misuse | 2 | 2 | 4 | 1. The software application will be designed in such a way that the color combinations used are visibile and legible for a normal human eye | Design Control | Design Control | 1 | 1 | 1 | NA
|  |  | Based on the upgrades the software feature may not perform as expected | R004 | Device malfunction
|  |  | The output of the algorithm may be inaccurate |  | False Positive
False Negative
|  |  | The ECG morphology can me misinterpreted by the user | R001 / R005 | 1. User Annoyance 2. Misdiagnosis | 3 | 4 | 12 | The screen resolution of the smart device will be taken into account while designing the software application 2. Clear instruction will be given in the user manual about the intended use of the device | Software design control | Design Control | 2 | 1 | 2 | NA
|  |  | 1. The user might take unnecessary medical advice from physician 2. The user has to go through unwanted tests and can get stressed | R001 / R005 | 1. User Annoyance 2. Misdiagnosis | 4 | 2 | 8 | 1. The software application for arrhythmia classification will undergo 60601-2-47 regulatory compliance for assuring the quality of ECG 2. The user manual will clearly postulate the intended used of the software application and say that it is not intended for diagnostic purpose | Design and instructions to use | Regulatory compliance, design control and instructions to use | 3 | 2 | 6 | NA
|  |  | The algorithm may not perform accurately leading to inaccurate output |  | False Positive
False Negative
|  |  | The algorithm may not perform accurately leading to inaccurate output |  | False Positive
False Negative
|  |  | Algorithm will not process the data |  | Delay in diagnosis
|  |  | Algorithm may not perform as intended |  | False Positive
False Negative